## Description
COMP 5700/5703/6700/6706 -- Software Process
Objective: | to gain experience with estimating size and effort.
Assignment: | The worksheets in this assignment provide you with a hypothetical historical development database as well as with a forecast of standard components for a hypothetical project. Please use this information to determine the size and effort of the project.
Notes: | - This homework assignment is be accomplished individually
Deliverables: | - This spreadsheet with "Solution" completed.
- (Optional) Explanatory calculations on worksheets "Calc-1", "Calc-2", etc.
- When complete, upload the spreadsheet to Canvas
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, right-click on the worksheet tab and select unprotect.

## Process
Process Script
Entry |  | - this spreadsheet
Tasks |  | see lecture notes
Exit |  | - complete "Assignment" worksheet
- (optional) intermediate calculations
Quality checks
General
Are all regions highlighted in yellow complete? (Either with a value, or NA if the cell is not applicable. No units of measure.)
Are supporting calculations understandable?
Size matrix
Are zero-method components ignored?
Are buckets sized by a log-normal distribution?
Component sizing
Has each new component been given a relative size?
Are new components sized according to the size matrix?
Are base components accounted for?
Size and effort calculations
Is effort based on the new and modified components?
Is productivity calcuated in LOC/hr?
Are correlation values based on correct data sets?
Is the range calculation valid? It is correct?
Does the Lower Prediction Interval (LPI) represent a valid value?
Useful Excel Functions
| correl | parms: | x's, y's
|  | returns: | correlation coefficient
|  | example: | given the data at right, | X | Y
|  |  | "=CORREL(F83:F88,G83:G88)" | 1 | 2
|  |  | yields | 2 | 4
|  |  | 0.98372 | 4 | 8
|  |  |  | 5 | 10
|  |  |  | 6 | 12
|  |  |  | 7 | 17
| average | parms: | values
|  | returns: | average of the values
|  | example: | the average of the x's above is "=AVERAGE(F42:F47)", or |  |  | 4.1667
| stdev | parms: | values
|  | returns: | standard deviation of the values
|  | example: | the std of the x's above is "=STDEV(F42:F47)", or |  |  | 2.3166
| sum | parms: | values
|  | returns: | sum of the values
|  | example: | the sum of the x's above is "=SUM(F42:F47)", which yields |  |  | 25
| ln | parms: | value
|  | returns: | natural logarithm of the value
|  | example: | the natural logarithm of the value above is "=ln(I59)", which yields |  |  | 3.2189
| exp | parms: | power
|  | returns: | 2.718**power
|  | example: | the antilog of the natural log abve "=exp(I59)", which is |  |  | 25
| ceiling | parms: | value, places
|  | returns: | a value that is rounded up to the nearest significant digit
|  | example: | the integer ceiling of 4.1667 is "=ceiling(4.1667,1)", which is: |  |  | 5
| floor | parms: | value, places
|  | returns: | a value that is rounded down to the nearest significant digit
|  | example: | the integer floor of 4.1667 is "=floor(4.1667,1)", which is |  |  | 4

## Component History
Component History: The following is a record of historical components.
| Identifier | Total Loc | Methods | Type
| Component1 | 28 | 4 | I/O
| Component2 | 24 | 3 | Logic
| Component3 | 47 | 6 | Data
| Component4 | 66 | 7 | Data
| Component5 | 10 | 2 | Logic
| Component6 | 64 | 6 | Logic
| Component7 | 16 | 2 | Calculation
| Component8 | 47 | 5 | Logic
| Component9 | 10 | 2 | I/O
| Component10 | 73 | 9 | Calculation
| Component11 | 39 | 4 | I/O
| Component12 | 31 | 2 | I/O
| Component13 | 51 | 6 | I/O
| Component14 | 27 | 3 | Data
| Component15 | 20 | 2 | Logic
| Component16 | 14 | 1 | I/O
| Component17 | 19 | 3 | Logic
| Component18 | 19 | 3 | Data
| Component19 | 29 | 3 | Calculation
| Component20 | 23 | 2 | Logic
| Component21 | 64 | 6 | Logic
| Component22 | 16 | 1 | I/O
| Component23 | 96 | 11 | I/O
| Component24 | 11 | 2 | Logic
| Component25 | 19 | 3 | Logic
| Component26 | 81 | 8 | I/O
| Component27 | 38 | 3 | Calculation
| Component28 | 40 | 4 | Data
| Component29 | 37 | 4 | Logic
| Component30 | 35 | 3 | Calculation
| Component31 | 81 | 7 | Data
| Component32 | 15 | 1 | Data
| Component33 | 80 | 6 | Logic
| Component34 | 43 | 4 | Logic
| Component35 | 35 | 3 | I/O
| Component36 | 56 | 5 | Calculation
| Component37 | 35 | 4 | Data
| Component38 | 43 | 7 | Logic
| Component39 | 99 | 10 | I/O
| Component40 | 77 | 8 | Calculation
| Component41 | 40 | 3 | Calculation
| Component42 | 60 | 6 | Logic
| Component43 | 47 | 4 | Data
| Component44 | 113 | 11 | Logic
| Component45 | 45 | 4 | I/O
| Component46 | 5 | 1 | Calculation
| Component47 | 108 | 10 | Data
| Component48 | 61 | 8 | Data
| Component49 | 35 | 4 | Logic
| Component50 | 42 | 4 | I/O
| Component51 | 71 | 8 | Data
| Component52 | 42 | 4 | Calculation
| Component53 | 115 | 11 | Data
| Component54 | 13 | 2 | I/O
| Component55 | 35 | 4 | Logic
| Component56 | 28 | 4 | Data
| Component57 | 44 | 4 | Data
| Component58 | 5 | 1 | I/O
| Component59 | 86 | 7 | Data
| Component60 | 91 | 8 | Logic
| Component61 | 10 | 2 | I/O
| Component62 | 66 | 6 | Logic
| Component63 | 35 | 2 | I/O
| Component64 | 5 | 1 | Data
| Component65 | 45 | 3 | I/O
| Component66 | 96 | 9 | Data
| Component67 | 33 | 4 | Logic
| Component68 | 18 | 2 | Logic
| Component69 | 30 | 1 | Logic
| Component70 | 23 | 2 | Logic
| Component71 | 53 | 4 | I/O
| Component72 | 49 | 3 | Logic
| Component73 | 10 | 2 | Logic
| Component74 | 80 | 8 | Calculation
| Component75 | 108 | 11 | Calculation
| Component76 | 11 | 2 | Calculation
| Component77 | 16 | 2 | Calculation
| Component78 | 122 | 13 | Calculation
| Component79 | 48 | 4 | Logic
| Component80 | 5 | 1 | Logic
| Component81 | 42 | 4 | Logic
| Component82 | 47 | 5 | Logic
| Component83 | 25 | 3 | Logic
| Component84 | 106 | 12 | Data
| Component85 | 56 | 5 | Calculation
| Component86 | 50 | 7 | Logic
| Component87 | 35 | 0 | Data

## Project History
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea)
| Project1 | 592 | 761 | 1217 | 1270 | 4835
| Project2 | 484 | 557 | 627 | 1267 | 3111
| Project3 | 561 | 634 | 998 | 2597 | 3076
| Project4 | 492 | 467 | 695 | 1967 | 2533
| Project5 | 701 | 804 | 853 | 3244 | 3724
| Project6 | 450 | 508 | 528 | 1175 | 1175
| Project7 | 583 | 637 | 867 | 2328 | 3307
| Project8 | 571 | 630 | 714 | 1615 | 1789
| Project9 | 671 | 730 | 1079 | 2176 | 3183
| Project10 | 439 | 538 | 668 | 1063 | 1738
| Project11 | 556 | 556 | 836 | 1827 | 3379
| Project12 | 550 | 704 | 893 | 1143 | 3270
| Project13 | 615 | 683 | 664 | 1281 | 1783
| Project14 | 475 | 488 | 492 | 1585 | 2145
| Project15 | 558 | 605 | 805 | 2053 | 2674
| Project16 | 649 | 757 | 1269 | 2757 | 5133
| Project17 | 352 | 355 | 414 | 2086 | 1177
| Project18 | 479 | 547 | 353 | 1518 | 972
| Project19 | 577 | 606 | 799 | 1282 | 2255
| Project20 | 593 | 915 | 1075 | 3131 | 3180

## Activities
Activities: The following describes the to-date percentages for development time and defects.
| Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
| Analysis | 18% | 5% | 0%
| Architecture | 8% | 10% | 0%
| Project planning | 10% | 0% | 0%
| Interation Planning | 2% | 1% | 0%
| Construction | 30% | 77% | 30%
| Refactoring | 3% | 3% | 4%
| Review | 1% | 0% | 3%
| Integration Test | 7% | 0% | 63%
| Repatterning | 9% | 0% | 0%
| Postmortem | 4% | 0% | 0%
| Sandbox | 8% | 5% | 0%
| Total | 100% | 100% | 100%

## Architecture
Architecture: The following CRC cards describe the solution.
| Component Name | ForecastedComponent01
| Design Approach | OO
Superclass
| Component Type | I/O
| Collaborators | ForecastedComponent02, ForecastedComponent05
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component51
| Component Name | ForecastedComponent02
| Design Approach | OO
| Superclass | ForecastedComponent06
| Component Type | Data
| Collaborators | ForecastedComponent03, ForecastedComponent04
| Operations | 7 methods
| Notes | The functionality of this component is available by deleting 17 LOC from, modifying 16 LOC of, and adding 29 LOC to Component86 as well as adding 1 new method(s) to Component86
| Component Name | ForecastedComponent03
| Design Approach | OO
Superclass
| Component Type | Data
Collaborators
| Operations | 5 methods
| Notes | The functionality of this component is available by deleting 14 LOC from, modifying 13 LOC of, and adding 21 LOC to Component70 as well as adding 1 new method(s) to Component70
| Component Name | ForecastedComponent04
| Design Approach | OO
Superclass
| Component Type | Data
Collaborators
| Operations | 4 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component75
| Component Name | ForecastedComponent05
| Design Approach | OO
Superclass
| Component Type | Calculation
Collaborators
| Operations | 4 methods
| Notes | The functionality of this component is available by deleting 12 LOC from, modifying 11 LOC of, and adding 20 LOC to Component42 as well as adding 1 new method(s) to Component42
| Component Name | ForecastedComponent06
| Design Approach | OO
Superclass
| Component Type | Data
Collaborators
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component58

## Solution
Name: | Hunter Donald
Username: | hzd0011
Instructor Assessment
Aspect | Possible Score | Earned Score | Comment
Size matrix | 10
Component sizing | 10
Size and effort calculations | 20
Total | 40 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a value from a drop-down menu; do not indicate units (such as "min", "hr", "LOC", etc.) Please do not leave any boxes blank; I will assume that an empty box means you did not answer the question.
Parameters
normal | Day 1
log-normal | Day 2
not applicable | Day 3
LOCE x Time | Day 4
LOCA x Time | Day 5
Productivity | Day 6
not applicable | Day 7
VS | Day 8
S | Day 9
M | Day 10
L | Day 11
VL | Day 12
not applicable | Day 13
Calculation | Day 14
Data | Day 15
IO | Day 16
Logic | Day 17
not applicable | Day 18
low | Day 19
medium | Day 20
high | Day 21
Decision D | Day 22
not applicable | Day 23
Day 24
Day 25
Day 26
Day 27
Day 28
Day 29
Day 30
Day 31
Never
Solution
Solution
Size matrix
| Low | Mid | High
VS | 0 | 5 | 6 | LOC/Method
S | 6 | 7 | 8 | LOC/Method
M | 8 | 9 | 11 | LOC/Method
L | 11 | 13 | 15 | LOC/Method
VL | 15 | 18 | Big | LOC/Method
Component sizing
Component | Raw New LOC
ForecastedComponent01 | 45 | LOC
ForecastedComponent02 | 52 | LOC
ForecastedComponent03 | 47 | LOC
ForecastedComponent04 | 36 | LOC
ForecastedComponent05 | 40 | LOC
ForecastedComponent06 | 45 | LOC
Size and effort calculations
Total raw size (LOCr) | 265 | LOC
Planned size (LOCp) | 384 | LOC
Lower prediction interval (LPI) | 282.9896 | LOC
Upper prediction interval (UPI) | 789.4054 | LOC
Confidence | medium
Productivity (Prod) | 17.4647 | LOC/hr
Planned effort (Ep) | 1320 | Minutes
Lower prediction interval (LPI) | 854.5455 | Minutes
Upper prediction interval (UPI) | 1905.3014 | Minutes
Confidence | medium
Best case lower prediction interval | 629.759 | Minutes
Worse case upper prediction interval | 3916.8106 | Minutes

## Calc-1
Supporting Calculations for
Size matrix
LOC/meth | ln(LOC/meth) |  | mean= | 2.2371
7 | 1.9459 | Component1 | std= | 0.33276
8 | 2.0794 | Component2
7.8333 | 2.0584 | Component3
9.4286 | 2.2437 | Component4
5 | 1.6094 | Component5
10.6667 | 2.3671 | Component6
8 | 2.0794 | Component7
9.4 | 2.2407 | Component8
5 | 1.6094 | Component9
8.1111 | 2.0932 | Component10
9.75 | 2.2773 | Component11
15.5 | 2.7408 | Component12
8.5 | 2.1401 | Component13
9 | 2.1972 | Component14
10 | 2.3026 | Component15
14 | 2.6391 | Component16
6.3333 | 1.8458 | Component17
6.3333 | 1.8458 | Component18
9.6667 | 2.2687 | Component19
11.5 | 2.4423 | Component20
10.6667 | 2.3671 | Component21
16 | 2.7726 | Component22
8.7273 | 2.1665 | Component23
5.5 | 1.7047 | Component24
6.3333 | 1.8458 | Component25
10.125 | 2.315 | Component26
12.6667 | 2.539 | Component27
10 | 2.3026 | Component28
9.25 | 2.2246 | Component29
11.6667 | 2.4567 | Component30
11.5714 | 2.4485 | Component31
15 | 2.7081 | Component32
13.3333 | 2.5903 | Component33
10.75 | 2.3749 | Component34
11.6667 | 2.4567 | Component35
11.2 | 2.4159 | Component36
8.75 | 2.1691 | Component37
6.1429 | 1.8153 | Component38
9.9 | 2.2925 | Component39
9.625 | 2.2644 | Component40
13.3333 | 2.5903 | Component41
10 | 2.3026 | Component42
11.75 | 2.4639 | Component43
10.2727 | 2.3295 | Component44
11.25 | 2.4204 | Component45
5 | 1.6094 | Component46
10.8 | 2.3795 | Component47
7.625 | 2.0314 | Component48
8.75 | 2.1691 | Component49
10.5 | 2.3514 | Component50
8.875 | 2.1832 | Component51
10.5 | 2.3514 | Component52
10.4545 | 2.347 | Component53
6.5 | 1.8718 | Component54
8.75 | 2.1691 | Component55
7 | 1.9459 | Component56
11 | 2.3979 | Component57
5 | 1.6094 | Component58
12.2857 | 2.5084 | Component59
11.375 | 2.4314 | Component60
5 | 1.6094 | Component61
11 | 2.3979 | Component62
17.5 | 2.8622 | Component63
5 | 1.6094 | Component64
15 | 2.7081 | Component65
10.6667 | 2.3671 | Component66
8.25 | 2.1102 | Component67
9 | 2.1972 | Component68
30 | 3.4012 | Component69
11.5 | 2.4423 | Component70
13.25 | 2.584 | Component71
16.3333 | 2.7932 | Component72
5 | 1.6094 | Component73
10 | 2.3026 | Component74
9.8182 | 2.2842 | Component75
5.5 | 1.7047 | Component76
8 | 2.0794 | Component77
9.3846 | 2.2391 | Component78
12 | 2.4849 | Component79
5 | 1.6094 | Component80
10.5 | 2.3514 | Component81
9.4 | 2.2407 | Component82
8.3333 | 2.1203 | Component83
8.8333 | 2.1785 | Component84
11.2 | 2.4159 | Component85
7.1429 | 1.9661 | Component86
0 |  | Component87

## Calc-2
Supporting Calculations for
Component sizing
Architecture | Estimation Basis | Relative Size | Modified LOC | Added LOC | Deleted LOC | Base LOC | New Methods | LOC/Method | New LOC | Total
Component 1 | Like Component 51 | M | 0 | 0 | 0 | 0 | 5 | 9 | 45 | 45
Component 2 | Component 86 + mods + 1 method | S | 16 | 29 | 17 | 45 | 1 | 7 | 7 | 52
Component 3 | Component 70 + mods + 1 method | L | 13 | 21 | 14 | 34 | 1 | 13 | 13 | 47
Component 4 | Like Component 75 | M | 0 | 0 | 0 | 0 | 4 | 9 | 36 | 36
Component 5 | Component 42 + mods + 1 method | M | 11 | 20 | 12 | 31 | 1 | 9 | 9 | 40
Component 6 | Like Component 58 | VS | 0 | 0 | 0 | 0 | 5 | 9 | 45 | 45
[9 empty] | LOCr= | 265

## Calc-3
Supporting calculations for
Size and effort calculations
sum(LOCa)/sum(LOCr)= | 1.4474
planned size= | 384 | LOC
LPI= | 282.9896 | LOC
UPI= | 789.4054 | LOC
confidence= | 0.55034 | medium
sum(Ea)/sum(LOCa)= | 3.4355 | minutes/LOC
productivity | 17.4647 | LOC/hr
effort planned | 1320 | minutes
LPI= | 854.5455 | minutes
UPI= | 1905.3014 | minutes
confidence= | 0.78072 | medium since LOC confidence is medium
UUPI= | 3916.8106 | minutes
LLPI= | 629.759 | minutes
|  |  |  | Ea/LOCa | LOCa/LOCr | LOCa/LOCr
|  |  |  | 3.9729 | 2.0557 | 2.0557
|  |  |  | 4.9617 | 1.2955 | 1.2955
|  |  |  | 3.0822 | 1.779 | 1.779
|  |  |  | 3.6446 | 1.4126 | 1.4126
|  |  |  | 4.3658 | 1.2168 | 1.2168
|  |  |  | 2.2254 | 1.1733 | 1.1733
|  |  |  | 3.8143 | 1.4871 | 1.4871
|  |  |  | 2.5056 | 1.2504 | 1.2504
|  |  |  | 2.95 | 1.608 | 1.608
|  |  |  | 2.6018 | 1.5216 | 1.5216
|  |  |  | 4.0419 | 1.5036 | 1.5036
|  |  |  | 3.6618 | 1.6236 | 1.6236
|  |  |  | 2.6852 | 1.0797 | 1.0797
|  |  |  | 4.3598 | 1.0358 | 1.0358
|  |  |  | 3.3217 | 1.4427 | 1.4427
|  |  |  | 4.0449 | 1.9553 | 1.9553
|  |  |  | 2.843 | 1.1761 | 1.1761
|  |  |  | 2.7535 | 0.73695 | 0.73695
|  |  |  | 2.8223 | 1.3847 | 1.3847
|  |  |  | 2.9581 | 1.8128 | 1.8128
|  |  | max= | 4.9617 | 2.0557 | 2.0557
|  |  | min= | 2.2254 | 0.73695 | 0.73695