## Description
COMP 5700/5703//6700/6706 -- Software Process
Iteration: | 1
Objective: | To gain experience with TDD
Product: | Write software to read navigational sightings and to adjust those sightings based on atmospheric conditions.
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.
| Via GitHub: | Push your code to GitHub Classroom
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Change Log | The "Reference to a Previous Change" column allows you to indicate that you are fixing a fix. The value in the column should be the number on the change log of the fix you are repairing.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Pre-project | • Accept invitation to GitHub Classroom
• Pull your GitHub CLassroom repo into your PyDev Eclipse project
• Grad students only: Set up an IBM Cloud microserver
|  |  |  | Analyze | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
|  |  |  | Plan Project | • Guess projected LOC | Plan
[5 empty] | • Guess projected effort (in minutes) | Plan
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
[5 empty] | • • • • Fix the defect and log it in the change log | Change Log
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
[5 empty] | • • • Fix the defect and log it in the change log | Change Log
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
• Commit all code to git
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Plan
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit all code to git
• Push to GitHub.com
• Upload spreadsheet to Canvas
|  |  |  | Monitor | • Record time spent in each activity. | Time Log
Minimal Guiding Indicators |  |  |  |  | • Record defects, changes to requirements. | Change Log
Cost: |  | -
Schedule: |  | Submitted on time
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Project Planning
Post Mortem
Release
Monitor/Cntrl
Construct
Not all components are constructed
Analyze

## Customer Needs
Customer Needs
Background: | We are developing a set of microservices for Sudoku. Each microservice receives its input as a Python dictionary represented by a URL-encoded query string and outputs its result as UTF-8 string of a Python dictionary.
Functional Specifications: | sudoku
|  | Abstraction: | sudoku is a backend HTTP microservice that manipulates a Sudoku grid based on parameters passed to it.
| method |  | description
|  | GET /sudoku | Performs an operation on a Sudoku grid, where the operation and any accompanying parameters are specified by the query portion of the URL
|  |  | Invocation pattern: | http://name-of-server.com/sudoku?op=create&level=1
|  |  |  | where | signifies
|  |  |  | name-of-server.com | name of the microservice provider
|  |  |  | sudoku | name of the microservice
|  |  |  | op | operation to perform ("create," in this particular case)
|  |  |  | level=1 | parameters used in performing the operation ("level," in this particular case)
|  |  | Parameters: | Parameters to the microservice are specified in the query portion of the URL and must be in URL-legal format. All parameters arrive unvalidated. The "op" parameter is mandatory.
|  |  |  | Note: | If names are duplicated in the query string, the leftmost value is associated with the name.
[5 empty] | Example: | ?op=op1&op=op2
results in
"op1" being used as the value of "op"
|  |  |  | Note: | Names in the query string may be designated as empty, in which case they have an empty string as a value.
[5 empty] | Example: | ?op=op1&parm1=&parm2=
results in
empty strings being used as the values of "parm1" and "parm2"
|  |  | Desired behavior (normal): | Performs the operation named by the 'op' parameter. Returns a string of a Python dictionary containing the results. Operations are:
|  |  |  | Operation Name | Operation Description
|  |  |  | op=create | Creates a partially-solved grid.
|  |  |  | op=isdone | Determines if the puzzle has been solved correctly.
|  |  |  | op=insert | Sets the content of a specific cell.
|  |  |  | op=solve | Solves a partially-complete grid.
A description of each operation is given in the "operation" section below.
|  |  | Desired behavior (errors): | If: | the query string contains no "op" parameter
|  |  |  | Action: | Return a dictionary element having a key of "status" and a value of "error: xxx", where xxx is a diagnostic string.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | State change: | No state is retained by the microservice.
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/sudoku?op=create
|  |  |  | Returns: | A string of a dictionary containing the results of the "create" operation
|  |  |  | Input: | http://name-of-server.com/sudoku?op=create&level=3
|  |  |  | Returns: | A string of a dictionary containing the results of the "create" operation
Invalid values
|  |  |  | Input: | http://name-of-server.com/sudoku
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/sudoku?level=0
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/sudoku?op=sudoku
|  |  |  | Returns: | {'status':'error: op is not a legal operation'}
|  |  |  | Input: | http://name-of-server.com/sudoku?op=
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  | Implementation note: | Server interface code parses the HTTP request query string into a python dictionary and passes the dictionary to _dispatch() which, in turn, calls the component associated with the specified operation. Upon completion, a dictionary containing results is returned to _dispatch() and converted to a string the HTTP response. You should not have to modify microservice.py nor dispatch.py. Modules for handling each of the operations have been stubbed and require your modification.
| operation |  | description
Iteration 1 Statement of Work➜ |  | op=create | Creates a partially-solved Sudoku grid of a specified dificulty.
|  |  | Relevant dictionary elements: | level | level is the amount of effort required to solve the grid. It is a string of an integer value in the range [1,5]. Optional, defaults to '3' if missing.
Dictionary elements not specified above are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the the following key-value pairs:
|  |  |  | key | content
|  |  |  | grid | This key-value pair models the Sudoku puzzle. The value is a list of 81 integers arranged in row-major order to form a 9 x 9 grid. Each value is in the range [-9,9]. Empty cells have a value of zero. Cells that are pre-populated with hints have negative values. The value of such cells is the the absolute value. The negative symbol indicates that cell contents can not be changed. See "Support Info" for examples.
[5 empty] | value of level | grid to return
[5 empty] | 1 | [-8, -1, -5, -7, -6, -9, -3, -2, 0, -4, -9, 0, 0, 0, -5, -8, -7, 0, 0, 0, -6, 0, -4, -8, 0, -9, -5, 0, -8, -1, 0, 0, -3, 0, 0, -2, 0, -5, 0, -1, -8, 0, -9, 0, -7, -7, -3, -9, -5, -2, -4, -6, -8, -1, -9, -4, 0, 0, 0, -7, 0, -1, -8, -5, -2, 0, -8, -9, 0, -4, -6, -3, -1, -6, 0, -4, -3, -2, -7, 0, 0]
[5 empty] | 2 | [0, -3, 0, 0, 0, -2, 0, -6, -5, -5, -8, 0, -1, -3, -4, 0, -2, -9, 0, -2, -7, 0, -5, 0, 0, 0, -1, 0, 0, -2, 0, 0, -9, 0, -1, -3, -8, -5, -9, 0, -7, -1, 0, -4, -2, -1, 0, 0, -6, -2, 0, 0, 0, -7, 0, 0, 0, 0, -4, -7, -2, -5, 0, -6, -7, -5, 0, 0, -8, 0, -9, 0, 0, -9, -4, -5, -6, 0, 0, -7, -8]
[5 empty] | 3 | [0, 0, -3, 0, 0, -7, 0, -2, 0, -4, 0, -7, 0, 0, -5, -3, 0, 0, 0, 0, -8, -9, 0, -6, -7, 0, -1, -8, 0, -2, -5, 0, 0, -6, 0, -4, 0, -7, 0, 0, -8, 0, -1, -5, 0, -5, 0, 0, -7, -6, 0, 0, 0, -9, 0, 0, -5, 0, 0, -9, 0, 0, -6, 0, -1, 0, -6, 0, 0, -2, -8, 0, 0, -2, -4, -1, -7, 0, -5, 0, 0]
[5 empty] | 4 | [0, -6, -7, 0, -2, 0, 0, 0, -3, 0, -8, 0, -7, 0, -3, 0, 0, -6, -1, 0, 0, 0, 0, 0, 0, -7, 0, 0, -5, 0, 0, -3, 0, 0, 0, -8, -8, 0, 0, 0, -4, 0, 0, 0, -1, -4, 0, 0, 0, -6, 0, 0, -5, 0, -3, 0, 0, 0, 0, 0, 0, 0, -2, -6, 0, 0, -2, 0, -4, 0, -3, 0, -5, 0, 0, 0, -9, 0, -8, -4, 0]
[5 empty] | 5 | [-2, 0, 0, 0, -5, 0, -9, -1, 0, -6, 0, 0, 0, 0, -8, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, -3, 0, 0, -2, -4, 0, 0, 0, 0, 0, 0, 0, 0, 0, -4, 0, 0, 0, 0, -7, 0, -9, -3, 0, -1, 0, -5, 0, 0, 0, 0, 0, 0, 0, -7, 0, 0, -2, 0, -1, 0, 0, -3, 0, 0, -5, 0, -4, 0, 0, -6, 0, 0, 0, 0, 0]
Iteration note: The objective of iteration 1 is to return a specific grid for each level. Generation of original grids will take place in a later iteration.
|  |  |  | integrity | This key-value pair assures the integrity of the grid data. Its value is the sha256 hash hexdigest of the string created by concatenating the string value of each of the grid cells in column-major order. See "Support Info" for examples.
Iteration note: This is an initial integrity check that will be changed in a later iteration.
|  |  |  | status | 'ok'
|  |  | Desired behavior (errors): | If: | any dictionary element violates the description above
|  |  |  | Action: | Return a dictionary element having a key of "status" and a value of "error: xxx", where xxx is an appropriate diagnostic string.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | Sample results | Note: The sample inputs and outputs are intended to be illustrative, not as a comprehensive acceptance test suite.
Valid
|  |  |  | Input: | http://name-of-server.com/sudoku?op=create&level=1
|  |  |  | Returns: | {'grid': [-8, -1, -5, -7, -6, -9, -3, -2, 0, -4, -9, 0, 0, 0, -5, -8, -7, 0, 0, 0, -6, 0, -4, -8, 0, -9, -5, 0, -8, -1, 0, 0, -3, 0, 0, -2, 0, -5, 0, -1, -8, 0, -9, 0, -7, -7, -3, -9, -5, -2, -4, -6, -8, -1, -9, -4, 0, 0, 0, -7, 0, -1, -8, -5, -2, 0, -8, -9, 0, -4, -6, -3, -1, -6, 0, -4, -3, -2, -7, 0, 0],'integrity': '634dd6769e9b9a53ee4416edb9790684ac18dcbde5b879260610ff27794b66f5','status':'ok'}
|  |  |  | Input: | http://name-of-server.com/sudoku?op=create
|  |  |  | Returns: | {'grid': [0, 0, -3, 0, 0, -7, 0, -2, 0, -4, 0, -7, 0, 0, -5, -3, 0, 0, 0, 0, -8, -9, 0, -6, -7, 0, -1, -8, 0, -2, -5, 0, 0, -6, 0, -4, 0, -7, 0, 0, -8, 0, -1, -5, 0, -5, 0, 0, -7, -6, 0, 0, 0, -9, 0, 0, -5, 0, 0, -9, 0, 0, -6, 0, -1, 0, -6, 0, 0, -2, -8, 0, 0, -2, -4, -1, -7, 0, -5, 0, 0],'integrity': 'b594924588d873f60df054a64a7bfaa1d4196ab1d2000f1788a453c1765b05b8','status':'ok'}
Invalid
|  |  |  | Input: | http://name-of-server.com/sudoku?op=create&level=0
|  |  |  | Returns: | {'status':'error: invalid level'}
Future Iteration ➜ |  | op=isdone | Determines if the puzzle has been solved correctly.
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | op=insert | Sets the content of a specific cell.
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | op=solve | Solves a partially-solved grid.
|  |  | Desired behavior (normal): | Currently stubbed

## Spec Notes (hidden)
Specification Notes

## Support Info
Sample Grids
Level | 1
|  | 8 | 1 | 5 | 7 | 6 | 9 | 3 | 2 |  | Input: | http://name-of-server.com/sudoku?op=create&level=1
|  | 4 | 9 |  |  |  | 5 | 8 | 7 |  | Output: | {
|  |  |  | 6 |  | 4 | 8 |  | 9 | 5 |  | 'grid': | [-8, -1, -5, -7, -6, -9, -3, -2, 0, -4, -9, 0, 0, 0, -5, -8, -7, 0, 0, 0, -6, 0, -4, -8, 0, -9, -5, 0, -8, -1, 0, 0, -3, 0, 0, -2, 0, -5, 0, -1, -8, 0, -9, 0, -7, -7, -3, -9, -5, -2, -4, -6, -8, -1, -9, -4, 0, 0, 0, -7, 0, -1, -8, -5, -2, 0, -8, -9, 0, -4, -6, -3, -1, -6, 0, -4, -3, -2, -7, 0, 0],
|  |  | 8 | 1 |  |  | 3 |  |  | 2 |  | 'integrity': | '634dd6769e9b9a53ee4416edb9790684ac18dcbde5b879260610ff27794b66f5',
|  |  | 5 |  | 1 | 8 |  | 9 |  | 7 |  | 'status': | 'ok'
|  | 7 | 3 | 9 | 5 | 2 | 4 | 6 | 8 | 1 |  | }
|  | 9 | 4 |  |  |  | 7 |  | 1 | 8
|  | 5 | 2 |  | 8 | 9 |  | 4 | 6 | 3 | Note: | The value of "integrity" is the sha256 hexdigest of "-8-4000-7-9-5-1-1-90-8-5-3-4-2-6-50-6-10-9000-7000-1-50-8-4-60-40-8-20-9-3-9-5-8-30-4-70-2-3-800-9-60-4-7-2-7-900-8-1-6000-5-2-7-1-8-30"
|  | 1 | 6 |  | 4 | 3 | 2 | 7
Level | 2
|  |  | 3 |  |  |  | 2 |  | 6 | 5 | Input: | http://name-of-server.com/sudoku?op=create&level=2
|  | 5 | 8 |  | 1 | 3 | 4 |  | 2 | 9 | Output: | {
|  |  | 2 | 7 |  | 5 |  |  |  | 1 |  | 'grid': | [0, -3, 0, 0, 0, -2, 0, -6, -5, -5, -8, 0, -1, -3, -4, 0, -2, -9, 0, -2, -7, 0, -5, 0, 0, 0, -1, 0, 0, -2, 0, 0, -9, 0, -1, -3, -8, -5, -9, 0, -7, -1, 0, -4, -2, -1, 0, 0, -6, -2, 0, 0, 0, -7, 0, 0, 0, 0, -4, -7, -2, -5, 0, -6, -7, -5, 0, 0, -8, 0, -9, 0, 0, -9, -4, -5, -6, 0, 0, -7, -8],
|  |  |  | 2 |  |  | 9 |  | 1 | 3 |  | 'integrity': | '39a4fbe2283d82b8dff98f36e6fcb09e6071653a77795e9527b26f90b4ad0d26',
|  | 8 | 5 | 9 |  | 7 | 1 |  | 4 | 2 |  | 'status': | 'ok'
|  | 1 |  |  | 6 | 2 |  |  |  | 7 |  | }
[6 empty] | 4 | 7 | 2 | 5
|  | 6 | 7 | 5 |  |  | 8 |  | 9 |  | Note: | The value of "integrity" is the sha256 hexdigest of "0-500-8-10-60-3-8-20-500-7-900-7-2-900-5-40-1000-600-50-3-50-7-2-40-6-2-40-9-10-7-80000000-200-6-20-1-40-5-9-7-5-9-1-3-2-700-8"
|  |  | 9 | 4 | 5 | 6 |  |  | 7 | 8
Level | 3
|  |  |  | 3 |  |  | 7 |  | 2 |  | Input: | http://name-of-server.com/sudoku?op=create&level=3
|  | 4 |  | 7 |  |  | 5 | 3 |  |  | Output: | {
|  |  |  | 8 | 9 |  | 6 | 7 |  | 1 |  | 'grid': | [0, 0, -3, 0, 0, -7, 0, -2, 0, -4, 0, -7, 0, 0, -5, -3, 0, 0, 0, 0, -8, -9, 0, -6, -7, 0, -1, -8, 0, -2, -5, 0, 0, -6, 0, -4, 0, -7, 0, 0, -8, 0, -1, -5, 0, -5, 0, 0, -7, -6, 0, 0, 0, -9, 0, 0, -5, 0, 0, -9, 0, 0, -6, 0, -1, 0, -6, 0, 0, -2, -8, 0, 0, -2, -4, -1, -7, 0, -5, 0, 0],
|  | 8 |  | 2 | 5 |  |  | 6 |  | 4 |  | 'integrity': | 'b594924588d873f60df054a64a7bfaa1d4196ab1d2000f1788a453c1765b05b8',
|  |  | 7 |  |  | 8 |  | 1 | 5 |  |  | 'status': | 'ok'
|  | 5 |  |  | 7 | 6 |  |  |  | 9 |  | }
|  |  |  | 5 |  |  | 9 |  |  | 6
|  |  | 1 |  | 6 |  |  | 2 | 8 |  | Note: | The value of "integrity" is the sha256 hexdigest of "0-40-80-50000000-700-1-2-3-7-8-200-50-400-9-50-70-6-10000-8-600-7-7-5-6000-9000-3-7-6-100-2-5-2000-500-8000-1-40-9-600"
|  |  | 2 | 4 | 1 | 7 |  | 5
Level | 4
|  |  | 6 | 7 |  | 2 |  |  |  | 3 | Input: | http://name-of-server.com/sudoku?op=create&level=4
|  |  | 8 |  | 7 |  | 3 |  |  | 6 | Output: | {
|  | 1 | [6 empty] | 7 |  |  | 'grid': | [0, -6, -7, 0, -2, 0, 0, 0, -3, 0, -8, 0, -7, 0, -3, 0, 0, -6, -1, 0, 0, 0, 0, 0, 0, -7, 0, 0, -5, 0, 0, -3, 0, 0, 0, -8, -8, 0, 0, 0, -4, 0, 0, 0, -1, -4, 0, 0, 0, -6, 0, 0, -5, 0, -3, 0, 0, 0, 0, 0, 0, 0, -2, -6, 0, 0, -2, 0, -4, 0, -3, 0, -5, 0, 0, 0, -9, 0, -8, -4, 0],
|  |  | 5 |  |  | 3 |  |  |  | 8 |  | 'integrity': | '0ea83ad27c27241477102e2377f1bb14cc2f8c6125fbc85fab972c9ab0661319',
|  | 8 |  |  |  | 4 |  |  |  | 1 |  | 'status': | 'ok'
|  | 4 |  |  |  | 6 |  |  | 5 |  |  | }
|  | 3 | [7 empty] | 2
|  | 6 |  |  | 2 |  | 4 |  | 3 |  | Note: | The value of "integrity" is the sha256 hexdigest of "00-10-8-4-3-6-5-6-80-500000-7000000000-700000-20-200-3-4-600-90-300000-4000000000-800-700-50-3-4-3-60-8-10-200"
|  | 5 |  |  |  | 9 |  | 8 | 4
Level | 5
|  | 2 |  |  |  | 5 |  | 9 | 1 |  | Input: | http://name-of-server.com/sudoku?op=create&level=5
|  | 6 |  |  |  |  | 8 |  |  |  | Output: | {
[9 empty] | 3 |  |  | 'grid': | [-2, 0, 0, 0, -5, 0, -9, -1, 0, -6, 0, 0, 0, 0, -8, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, -3, 0, 0, -2, -4, 0, 0, 0, 0, 0, 0, 0, 0, 0, -4, 0, 0, 0, 0, -7, 0, -9, -3, 0, -1, 0, -5, 0, 0, 0, 0, 0, 0, 0, -7, 0, 0, -2, 0, -1, 0, 0, -3, 0, 0, -5, 0, -4, 0, 0, -6, 0, 0, 0, 0, 0],
|  |  | 2 | 4 | [7 empty] | 'integrity': | '110a79143bc7c2b66faff5e8fe895320d402e4f91dbbe6b969931228abb84242',
[5 empty] | 4 |  |  |  |  | 7 |  | 'status': | 'ok'
|  |  | 9 | 3 |  | 1 |  | 5 |  |  |  | }
[7 empty] | 7 |  |  | 2
|  |  | 1 |  |  | 3 |  |  | 5 |  | Note: | The value of "integrity" is the sha256 hexdigest of "-2-6000000-4000-20-90-10000-40-30000000-4000-6-50000-10-300-80000-700-90000-5000-10-30000-500000-70-2000"
|  | 4 |  |  | 6

## Assessment
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Hunter Donald
User name: |  | hzd0011
GitHub user name: |  | hzd0011
URL of microservice: |  |  |  | <-- Grad students only
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Grading rubric: Product Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Product satisfies all functional requirements, has insignificant nonfunctional requirement nonconformance
| AB | 90 | Product satisfies all functional requirements, has minor nonfunctional requiement nonconformance
| B | 85 | Product satisfies all functional requirements, has major nonfunctional requirement noncomformance
| BC | 80 | Product encounters minor functional deviations, has insignificant nonfunctional requirement nonconfirmance
| C | 75 | Product encounters minor functional deviations, has minor nonfunctional requirement nonconfirmance
| CD | 70 | Product encounters minor functional deviations, has major nonfunctional requirement nonconfirmance
| D | 65 | Product encounters multiple significant problems in functional and nonfunctional requirements
| F | 50 | Deliverables show lack of comprehension of concepts, or are incomplete
Grading rubic: Process Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Process has insignificant exceptions
| AB | 90 | Process has multiple minor exceptions
| B | 85 | Process has exceptions that obsure activity verification
| BC | 80 | Process has exceptions with historical data that affect the current project
| C | 75 | Process has exceptions that suggest lack of comprehension of concepts
| CD | 70 | Process has exceptions that bring into question the validity of the data
| D | 65 | Process has exceptions suggesting it wasn't followed.
| F | 50 | Deliverables are incomplete
Quality checks |  |  | changes from the previous assignment are in red
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Were initial expected results determined in advance of actual results?
Are the expected results sufficiently detailed for an independent party to test the software?
Are the expected results correct?
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Are acceptance tests written to the level of boundary value analysis?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the assignment requirements?
Does the code follow the prescribed directory format (i.e., prod, test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been uploaded to Canvas?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Does the error count indicated the analysis of defects match your historical defect count?
Are checklist items answerable in "yes" or "no" terms?
Does your checklist reflect at least two common items from your defect log ?
Does your checklist contain more than "mom and apple pie" items?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code, new components, or reused code?
Is base code vs reuse code identified correctly?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Does the value of LOCa reflect effort expended on creating, adding, or modifying production code?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment6 | Assignment6
As of the end of |  |  | Assignment6
|  | Assignment6 | Assignment6 | All previous
Program Size (LOC) |  | LOCp | LOCa | LOCa
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
|  | Assignment6 | Assignment6 | All previous
Time In Phase (minutes) |  | Ep | Ea | Ea | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
All previous
Changes traced to the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
App previous
Changes implemented in the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS
S
M
L
VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Trends
Productivity= |  | LOC/hr
Average size= |  | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
dispatch |  |  |  | Logic | -
|  |  |  | - | -
|  |  |  | - | - |  |  | `
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 0
[6 empty] | Std= | 0
Note on C57: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C61: Estimate of the number of previously-written components that require modification
Note on C62: Estimate of the number of entirely new components

## Review (hidden)
Review
Standards
Start date: | 2000-01-01 |  | Grades: |  |  | AA
End date: | 2020-01-01 |  |  |  |  | A
Phases: | Analysis |  |  |  |  | AB
| Architecture |  |  |  |  | B
| Planning |  |  |  |  | BC
| Construction |  |  |  |  | C
| Refactoring |  |  |  |  | CD
| Review |  |  |  |  | D
| Integration Test |  |  |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration |  |  | NA
| Build |  |  |  |  | 1
| Product syntax |  |  |  |  | 2
| Product logic |  |  |  |  | 3
| Product interface |  |  |  |  | 4
| Product checking |  |  |  |  | 5
| Test syntax |  |  |  |  | 6
| Test logic |  |  |  |  | 7
| Test interface |  |  |  |  | 8
| Test checking |  |  |  |  | 9
| Bad Smell |  |  |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
Defect Pareto Analysis (taken from all defects to date)
| Type | Description |  | Count of Occurrences | %
| Requirements Change | Changes to requirements
| Requirements Clarification | Clarifications to requirements
| Product syntax | Syntax flaws in the deliverable product
| Product logic | Logic flaws in the deliverable product
| Product interface | Flaws in the interface of a component of the deliverable product
| Product checking | Flaws with boundary/type checking within a component of the deliverable product
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description)
|  |  | Total | 0 | 0%
Code Review Checklist
| Item |  |  | Number of times this item detected a defect during review

## Acceptance
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0
End date: | 73051 |  |  | A | 0.95 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0
| Architect | High-level design |  | B | 0.85 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 43747
| Refactor | Restructure internal design |  | D | 0.65 | 43748
| Review | Examine test code for risk mitigation |  | F | 0.5 | 43749
| Integration test | End-to-end test of components to date |  |  |  | 43750
| Repattern | Restructure external design |  |  |  | 43751
| Postmortem | Capture post-development statistics |  |  |  | 43752
| Sandbox | Prove ideas, try concepts |  |  |  | 43753
43754
43755
43756
#REF!
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | #REF!
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | #REF!
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | #REF!
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | #REF!
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | #REF!
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | #REF!
| Test syntax | Syntax flaws in the test code |  | 6 |  | #REF!
| Test logic | Logic flaws in the test code |  | 7 |  | #REF!
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | #REF!
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | #REF!
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | #REF!
Y/N: | Yes |  |  | Passed | 0 | #REF!
| No |  |  | Passed with issues | 0 | 43770
Proxy Types: | - |  |  | Failed | Base | 43771
| Calculation |  |  | Not tested | New | 43772
| Data |  |  | Not applicable | Reusable | 43773
| I/O |  |  |  |  | 43774
| Logic |  |  |  |  | 43775
43776
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
| 0 | 0 | 0 | 0 |  | VL
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
op=create
op=isdone
op=insert
op=solve
Requirement | Test | Expected Results |  | Actual Results | Issues
op=create | create with nominal level: op=create&level=3 | {'grid': [0, 0, -3, 0, 0, -7, 0, -2, 0, -4, 0, -7, 0, 0, -5, -3, 0, 0, 0, 0, -8, -9, 0, -6, -7, 0, -1, -8, 0, -2, -5, 0, 0, -6, 0, -4, 0, -7, 0, 0, -8, 0, -1, -5, 0, -5, 0, 0, -7, -6, 0, 0, 0, -9, 0, 0, -5, 0, 0, -9, 0, 0, -6, 0, -1, 0, -6, 0, 0, -2, -8, 0, 0, -2, -4, -1, -7, 0, -5, 0, 0],'integrity': 'b594924588d873f60df054a64a7bfaa1d4196ab1d2000f1788a453c1765b05b8','status':'ok'} |  | Passed
op=create | create with nominal level: op=create&level=1 | {'grid': [-8, -1, -5, -7, -6, -9, -3, -2, 0, -4, -9, 0, 0, 0, -5, -8, -7, 0, 0, 0, -6, 0, -4, -8, 0, -9, -5, 0, -8, -1, 0, 0, -3, 0, 0, -2, 0, -5, 0, -1, -8, 0, -9, 0, -7, -7, -3, -9, -5, -2, -4, -6, -8, -1, -9, -4, 0, 0, 0, -7, 0, -1, -8, -5, -2, 0, -8, -9, 0, -4, -6, -3, -1, -6, 0, -4, -3, -2, -7, 0, 0],'integrity': '634dd6769e9b9a53ee4416edb9790684ac18dcbde5b879260610ff27794b66f5','status':'ok'} |  | Passed
op=create | create with nominal level: op=create&level=2 | {'grid': [0, -3, 0, 0, 0, -2, 0, -6, -5, -5, -8, 0, -1, -3, -4, 0, -2, -9, 0, -2, -7, 0, -5, 0, 0, 0, -1, 0, 0, -2, 0, 0, -9, 0, -1, -3, -8, -5, -9, 0, -7, -1, 0, -4, -2, -1, 0, 0, -6, -2, 0, 0, 0, -7, 0, 0, 0, 0, -4, -7, -2, -5, 0, -6, -7, -5, 0, 0, -8, 0, -9, 0, 0, -9, -4, -5, -6, 0, 0, -7, -8],'integrity': '39a4fbe2283d82b8dff98f36e6fcb09e6071653a77795e9527b26f90b4ad0d26','status':'ok'} |  | Passed
op=create | create with nominal level: op=create&level=4 | {'grid': [0, -6, -7, 0, -2, 0, 0, 0, -3, 0, -8, 0, -7, 0, -3, 0, 0, -6, -1, 0, 0, 0, 0, 0, 0, -7, 0, 0, -5, 0, 0, -3, 0, 0, 0, -8, -8, 0, 0, 0, -4, 0, 0, 0, -1, -4, 0, 0, 0, -6, 0, 0, -5, 0, -3, 0, 0, 0, 0, 0, 0, 0, -2, -6, 0, 0, -2, 0, -4, 0, -3, 0, -5, 0, 0, 0, -9, 0, -8, -4, 0],'integrity': '0ea83ad27c27241477102e2377f1bb14cc2f8c6125fbc85fab972c9ab0661319','status':'ok'} |  | Passed
op=create | create with nominal level: op=create&level=5 | {'grid': [-2, 0, 0, 0, -5, 0, -9, -1, 0, -6, 0, 0, 0, 0, -8, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, -3, 0, 0, -2, -4, 0, 0, 0, 0, 0, 0, 0, 0, 0, -4, 0, 0, 0, 0, -7, 0, -9, -3, 0, -1, 0, -5, 0, 0, 0, 0, 0, 0, 0, -7, 0, 0, -2, 0, -1, 0, 0, -3, 0, 0, -5, 0, -4, 0, 0, -6, 0, 0, 0, 0, 0],'integrity': '110a79143bc7c2b66faff5e8fe895320d402e4f91dbbe6b969931228abb84242','status':'ok'} |  | Passed
op=create | create with out of bounds level: op=create&level=0 | {'status':'error: invalid level'} |  | Passed
op=create | create with out of bounds level: op=create&level=6 | {'status':'error: invalid level'} |  | Passed
op=create | create with string level: op=create&level="two" | {'status':'error: invalid level'} |  | Passed
op=create | create with float level: op=create&level=2.0 | {'status':'error: invalid level'} |  | Passed
op=create | create with empty level value: op=create&level='' | {'status':'error: invalid level'} |  | Passed
op=create | create with level parameter missing: op=create | {'grid': [0, 0, -3, 0, 0, -7, 0, -2, 0, -4, 0, -7, 0, 0, -5, -3, 0, 0, 0, 0, -8, -9, 0, -6, -7, 0, -1, -8, 0, -2, -5, 0, 0, -6, 0, -4, 0, -7, 0, 0, -8, 0, -1, -5, 0, -5, 0, 0, -7, -6, 0, 0, 0, -9, 0, 0, -5, 0, 0, -9, 0, 0, -6, 0, -1, 0, -6, 0, 0, -2, -8, 0, 0, -2, -4, -1, -7, 0, -5, 0, 0],'integrity': 'b594924588d873f60df054a64a7bfaa1d4196ab1d2000f1788a453c1765b05b8','status':'ok'} |  | Passed
Note on A50: Establish traceability between the tests and requirements.
Note on B50: Defines observable tests that have quantifiable resutls.
Note on C50: Specifies the result that that the test is anticipated to produce.
Note on E50: Defines the result of running the test in relation to the expected result.
Note on F50: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture (hidden)
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
2 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
3 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
4 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation (hidden)
Size Estimate
Constants |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 43756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 43747 | 0 | 0 | AM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 43748 | 1 | 5 | PM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review | Examine test code for risk mitigation |  | F | 0.5 | 43749 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration test | End-to-end test of components to date |  |  |  | 43750 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repattern | Restructure external design |  |  |  | 43751 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Postmortem | Capture post-development statistics |  |  |  | 43752 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sandbox | Prove ideas, try concepts |  |  |  | 43753 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43754 | 7 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43755 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43756 | 9 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43757 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 43758 | 11 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 43759 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 43760 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 43761 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 43762 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 43763 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 43764 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 43765 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 43766 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 43767 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 43768 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y/N: | Yes |  |  | Passed | 0 | 43769 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No |  |  | Passed with issues | 0 | 43770 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 43771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Calculation |  |  | Not tested | New | 43772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data |  |  | Not applicable | Reusable | 43773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I/O |  |  |  |  | 43774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logic |  |  |  |  | 43775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Estimated | [10 empty] | Actual
|  |  | Changes to existing code | [5 empty] | New code |  |  |  |  | Changes to existing code | [5 empty] | New code
Component | Type | Relative Size | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCr) |  | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCa) | Is this component reusable?
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
Totals |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Size Calculation
0
0
0
|  | 0 | Low
Effort Calculation
0
0
0
0
|  | 0 | Low
Estimation: | LOCr= |  | 0
| LOCp= | [12 empty] | Actual: | LOCa= | 0
Ep=
Rationale for override:

## ArcEstimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | LOCr | Reuseable? |  |  | Method Count | LOCa | Reusable?
Totals |  | 0 |  |  |  |  | 0
Actual
Reused Parts | LOC
Totals | 0
Size Calculation
#REF!
0
#REF!
|  | 0 | Low
Effort Calculation
0
#REF!
#REF!
#REF!
|  | 0 | Low
Estimation | LOCr= |  | 0
| LOCp= |  | 0 |  |  | LOCa= | 0
| Ep= |  | 0
Rationale for override:
Note on G66: Indicate only new methods and LOC that resulted from effort. Do not count items that were previously base code and were refactored into new components.

## Plan
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  |  |  | 0
Lines deleted from Base |  |  |  | 0
Lines modified from Base |  |  |  | 0
Lines added to Base |  |  |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 40 | 32 | 32
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 70 | 70 | 33.33%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 30 | 30 | 14.29%
Construct |  |  | 95 | 95 | 45.24%
Refactor |  |  | 10 | 10 | 4.762%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 5 | 5 | 2.381%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  | 360 | 210 | 210 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 5 | 5 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 3 | 3 | 60%
Refactor |  |  | 2 | 2 | 40%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Iterations (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10
Base Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
New Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effort: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS
| Iteration Number | Planned Effort (minutes) | Cumulative Planned Effort | Planned Velocity | Cumulative Planned Velocity | Planned Completion Date
| 1 |  | 0 |  | 0
| 2 |  | 0 |  | 0
| 3 |  | 0 |  | 0
| 4 |  | 0 |  | 0
| 5 |  | 0 |  | 0
| 6 |  | 0 |  | 0
| 7 |  | 0 |  | 0
| 8 |  | 0 |  | 0
| 9 |  | 0 |  | 0
| 10 |  | 0 |  | 0
Calendar
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity
| 1 | due date - 24 |  | 0 |  | 0
| 2 | due date - 23 |  | 0 |  | 0
| 3 | due date - 22 |  | 0 |  | 0
| 4 | due date - 21 |  | 0 |  | 0
| 5 | due date - 20 |  | 0 |  | 0
| 6 | due date - 19 |  | 0 |  | 0
| 7 | due date - 18 |  | 0 |  | 0
| 8 | due date - 17 |  | 0 |  | 0
| 9 | due date - 16 |  | 0 |  | 0
| 10 | due date - 15 |  | 0 |  | 0
| 11 | due date - 14 |  | 0 |  | 0
| 12 | due date - 13 |  | 0 |  | 0
| 13 | due date - 12 |  | 0 |  | 0
| 14 | due date - 11 |  | 0 |  | 0
| 15 | due date - 10 |  | 0 |  | 0
| 16 | due date - 9 |  | 0 |  | 0
| 17 | due date - 8 |  | 0 |  | 0
| 18 | due date - 7 |  | 0 |  | 0
| 19 | due date - 6 |  | 0 |  | 0
| 20 | due date - 5 |  | 0 |  | 0
| 21 | due date - 4 |  | 0 |  | 0
| 22 | due date - 3 |  | 0 |  | 0
| 23 | due date - 2 |  | 0 |  | 0
| 24 | due date - 1 |  | 0 |  | 0
| 25 | due date |  | 0 |  | 0
| 26 | due date + 1 |  | 0 |  | 0
| 27 | due date + 2 |  | 0 |  | 0
| 28 | due date + 3 |  | 0 |  | 0
| 29 | due date + 4 |  | 0 |  | 0
| 30 | due date + 5 |  | 0 |  | 0
| 31 | due date + 6 |  | 0 |  | 0
| 32 | due date + 7 |  | 0 |  | 0
| 33 | due date + 8 |  | 0 |  | 0
| 34 | due date + 9 |  | 0 |  | 0
| 35 | due date + 10 |  | 0 |  | 0
| 36 | due date + 11 |  | 0 |  | 0
| 37 | due date + 12 |  | 0 |  | 0
| 38 | due date + 13 |  | 0 |  | 0
| 39 | due date + 14 |  | 0 |  | 0
| 40 | due date + 15 |  | 0 |  | 0
| 41 | due date + 16 |  | 0 |  | 0
| 42 | due date + 17 |  | 0 |  | 0

## Summary (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to show how much production code you plan to write and the amount of time to write it. Values are extracted from the Estimation tab.
Program Size (LOC) |  | Plan | Actual | To Date
LOC |  | 0 | 0 | 0
LOCa |  |  |  | 0
Lines added to Base |  | 0 |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 0 |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  | 0 | 70 | 70 | 33.33%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 30 | 30 | 14.29%
Construct |  | 0 | 95 | 95 | 45.24%
Refactor |  | 0 | 10 | 10 | 4.762%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 5 | 5 | 2.381%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 210 | 210 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 5 | 5 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 3 | 3 | 60%
Refactor |  |  | 2 | 2 | 40%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Note on C50: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C51: Count of the number of lines of reused source code
Note on C52: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C55: Number of reusable components that will be reused.
Note on C56: Estimate of the number of previously-delivered components that will be used.
Note on C57: Estimate of the number of new components to be built.

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | #REF! | 0 | 0
New lines of production code |  | #REF! | 0 | 0
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analyze |  | 0 | 70 | 70 | 1400%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 30 | 30 | 600%
Construct |  | 0 | 95 | 95 | 1900%
Refactor |  | 0 | 10 | 10 | 200%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 5 | 5 | 100%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 210 | 210 | 4200%
Changes traced to the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1
Changes implemented in the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1

## Change Log
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 43756 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 43747 | 1 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 43748 | 2 | 5
| Review | Examine test code for risk mitigation |  | F | 0.5 | 43749 | 3 | 10
| Integration test | End-to-end test of components to date |  |  |  | 43750 | 4 | 15
| Repattern | Restructure external design |  |  |  | 43751 | 5 | 20
| Postmortem | Capture post-development statistics |  |  |  | 43752 | 6 | 25
| Sandbox | Prove ideas, try concepts |  |  |  | 43753 | 7 | 30
| Previous Project |  |  |  |  | 43754 | 8 | 35
[6 empty] | 43755 | 9 | 40
[6 empty] | 43756 | 10 | 45
[6 empty] | 43757 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 43758 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 43759 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 43760 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 43761 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 43762 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 43763 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 43764 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 43765 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 43766 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 43767 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 43768 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 43769 | 23 | 0
| No |  |  | Passed with issues | 0 | 43770 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 43771 | 0 | 0
| Calculation |  |  | Not tested | New | 43772 | 0 | 0
| Data |  |  | Not applicable | Reusable | 43773 | 0 | 0
| I/O |  |  |  |  | 43774 | 0 | 0
| Logic |  |  |  |  | 43775 | 0 | 0
[6 empty] | 43776 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Iteration Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1 | 2019-10-17 | Product logic | Construct | 1 | Construct | 1 | 3 |  | Moved testing for empty level value to the beginning of all of the if statements because there was an error when executing the if statement without the level value
2 | 2019-10-17 | Product syntax | Construct | 1 | Construct | 1 | 5 |  | I used the wrong method call for isinstance which caused a green light test to fail. Once I changed to the correct method, the test passed.
3 | 2019-10-17 | Test logic | Construct | 1 | Construct | 1 | 2 |  | Removed test for level with None value.
4 | 2019-10-17 | Bad Smell | Construct | 1 | Refactor | 1 | 5 |  | Changed from checking if level is a float or string to checking if it is not an int.
5 | 2019-10-17 | Product syntax | Construct | 1 | Refactor | 1 | 5 |  | Updated production code to fit the coding standard.
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Time Log
Constants | [6 empty] | 0
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analyze | 0 | Identifying customer needs |  | AB | 0.9 | 0 | 0
| Architect | 0 | High-level design |  | B | 0.85 | 0 | 0
| Plan project | 0 | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0
| Plan iteration | 0 | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0
| Construct | 0 | Low-level design, coding, unit testing |  | CD | 0.7 | 43747 | 0
| Refactor | 0 | Restructure internal design |  | D | 0.65 | 43748 | 1
| Review | 0 | Examine test code for risk mitigation |  | F | 0.5 | 43749 | 2
| Integration test | 0 | End-to-end test of components to date |  |  |  | 43750 | 3
| Repattern | 0 | Restructure external design |  |  |  | 43751 | 4
| Postmortem | 0 | Capture post-development statistics |  |  |  | 43752 | 5
| Sandbox | 0 | Prove ideas, try concepts |  |  |  | 43753 | 6
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed | Base
| Calculation |  | Not tested |  |  | Not tested | New
| Data |  | Not applicable |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
|  | Activity |  | Meaning
|  | Analyze |  | Identifying customer needs
|  | Architect |  | High-level design
|  | Plan project |  | Determine actions/effort for project duration
|  | Plan iteration |  | Determine actions/effort this iteration
|  | Construct |  | Low-level design, coding, unit testing
|  | Refactor |  | Restructure internal design
|  | Review |  | Examine test code for risk mitigation
|  | Integration test |  | End-to-end test of components to date
|  | Repattern |  | Restructure external design
|  | Postmortem |  | Capture post-development statistics
|  | Sandbox |  | Prove ideas, try concepts
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2019-10-16 | 15 | 0 | 16 | 25 | 15 | 70 | Analyze | 1 | Read over the assignment and came up with acceptance tests.
2019-10-17 | 10 | 0 | 10 | 30 |  | 30 | Plan iteration | 1 | Filled in projected LOC and time effort.
2019-10-17 | 10 | 50 | 11 | 40 |  | 50 | Construct | 1 | Wrote the first 5 acceptance tests and production code to make them pass.
2019-10-17 | 12 | 25 | 13 | 20 | 10 | 45 | Construct | 1 | Wrote the remaining acceptance tests and production code to make them pass.
2019-10-17 | 13 | 20 | 13 | 25 |  | 5 | Refactor | 1 | Changed from checking if level is a float or string to checking if it is not an int.
2019-10-17 | 13 | 35 | 13 | 40 |  | 5 | Refactor | 1 | Updated production code to fit the coding standard.
2019-10-17 | 13 | 45 | 13 | 50 |  | 5 | Postmortem | 1 | Calculated LOC and filled in acceptance test actual results.

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1
2
3
4
5
Notes and Comments
1
2
3
4
5

## Coding Standard
Coding Standard
A coding standard provides a map so that the code generated by a group of programmers will be consistent and, therefore, easier to read and maintain.
File headings
Place a doc string at the beginning of each file. The doc string should state the purpose of the file's contents, the date the file was baselined, the date of any modifications subsequent to being baselined, and the name of the author. Each line of the doc string should be indented by four spaces. It can be delimited by either three double quotes or three single quotes. [Rationale: This provides identifying information for the file.]
Example
'''
Created on Aug 27, 2088
@author: David Umphress
'''
Use of docstrings elsewhere is optional. If used, they may be free form; i.e., this coding standard specifies no format.
Comments
Use # for comments other than doc strings. [Rationale: This style of commenting makes comments consistent across other programming languages.]
Example
# Return the answer to the universe
return 42
Do not include comments such as "#end if" to denote end of structural constructs. [Rationale: Indentation gives a visual cue to nesting; comments that indicate end of blocks of code decrease readability.]
Multiple assignment statements
Avoid multiple assignment statements. Use only in situations where readability would be significantly affected by using single assignment statements. [Rationale: Multiple logical lines per physical line result in an inaccurate LOC count.]
|  | Not OK | OK
|  | myVar1, myVar2 = 0, 1 | myVar1 = 0
myVar2 = 1
|  | import os, sys | import os
import sys
Spanning physical lines
Logical lines can span multiple physical lines. In such cases, the continuation lines must be indented one indentation beyond the initial line. Break lines after operators or commas. [Rationale: Indentation improves readability.]
Do not span strings over more than one physical line. In cases where a string won’t fit on a physical line, break the string into individual parts that will fit on a line and concatenate the parts. [Rationale: This simplifies construction of tools that count lines of code.]
|  | Not OK | OK
|  | myVar1 = myVar2 + myVar3 + \ | myVar1 = myVar2 + myVar3 + \
|  | myVar4 | myVar4;
|  | myString = '''multi-line | myString='multi-line ’ + \
|  | string''' | ‘string’
Blank lines
Use blank lines to break up related chunks of code. Use at least one blank line between all methods. [Rationale: Blank lines visually segment blocks of related code, thus making it more understandable.]
Code readability
Code should be as self-documenting as possible. For example:
· Identifiers should be given meaningful names that indicate purpose or use.
· Single letters should only be used as names for loop indices when mirroring a mathematical equation specified in the requirements, otherwise, loop indices should be given names that indicate their use.
· Magic numbers – meaning, numbers that appear without explanation in source code – are to be avoided. If they appear, they should be assigned to identifiers that describe their purpose.
· Comments should be used sparingly as an aid to understanding non-intuitive code structure, complex calculations, unique circumstances, etc. It should not be a substitute for unreadable code.
[Rationale: These practices improve comprehension of code.]
Identifier naming
Variables should follow a camel-case convention (i.e., the identifier consists of a series of words with the spaces removed; the beginning letter should be lower case; the beginning letter of each word should be uppercase.)
Class names should be nouns in camel-case, with the first letter capitalized.
Example
class MyClass
Function names and method names should be in camel-case, with the first letter in lower case. The name should connote action and thus should be a verb or verb phrase.
Example
def run()
def getValue()
Methods that retrieve a Boolean object state must use the prefix is in the method name.
Example
isEnabled()
Identifiers designated to be constant should be nouns in all upper case with words separated by an underscore. All other identifiers should be nouns in camel-case, with the first letter in lower case.
Multiple inheritance
Do not use multiple inheritance. [Rationale: This practice decreases understandability.]
File contents
Unless specified otherwise, each class should be stored in its own file. The name of the file should be the name of the class followed by a “.py” extension. For example, class “MyComponent” should be located in a file named “MyComponent.py”.
Test code should be placed in a file whose file name clearly reflects what component is being tested. In most cases, the file name will be the component name appended with “Test.py”. For example, “MyComponentTest.py” would contain the code that tests “MyComponent.py”.
File structure
Code should be developed in your IDE using the following directory/file structure:

## Counting Standard
Counting Standard
A counting standard defines how to determine the number of lines of code.
Each non-blank, non-comment, non-doc string line of production code counts as one line of code.
Example:
| ''' | doc string … not a line of code
| Created to demonstrate the counting standard | doc string … not a line of code
| Baselined: 1 Aug 2099 | doc string … not a line of code
| Modified: 29 Sep 2099 | doc string … not a line of code
| @author: D. Umphress | doc string … not a line of code
| ''' | doc string … not a line of code
| import something | line of code
blank line … not a line of code
| def fib(n): | line of code
| ''' fib(n) calculates the Fibbanacci value of n ''' | doc string … not a line of code
| prev = 0 | line of code
| next = 1 | line of code
blank line … not a line of code
| for i in range(n - 1): | line of code
| temp = next | line of code
| next = next + prev | line of code
| prev = temp | line of code
| return next | line of code
total lines of code in the file: 9
total number of components: 1
name: fib
component method count = 1
component LOC count= 8

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants | [5 empty] | 0
Start date: | 2000-01-01 |  |  | Grades: | AA | 100% |  |  | 2019-10-18
End date: | 2100-01-01 |  |  |  | A | 95%
Phases: | Analyze |  | Identifying customer needs |  | AB | 90%
| Architect |  | High-level design |  | B | 85%
| Plan project |  | Determine actions/effort for project duration |  | BC | 80%
| Plan iteration |  | Determine actions/effort this iteration |  | C | 75%
| Construct |  | Low-level design, coding, unit testing |  | CD | 70% | 2019-10-09 | 0 | 0 | AM
| Refactor |  | Restructure internal design |  | D | 65% | 2019-10-10 | 1 | 5 | PM
| Review |  | Examine test code for risk mitigation |  | F | 50% | 2019-10-11 | 2 | 10
| Integration test |  | End-to-end test of components to date |  |  |  | 2019-10-12 | 3 | 15
| Repattern |  | Restructure external design |  |  |  | 2019-10-13 | 4 | 20
| Postmortem |  | Capture post-development statistics |  |  |  | 2019-10-14 | 5 | 25
| Sandbox |  | Prove ideas, try concepts |  |  |  | 2019-10-15 | 6 | 30
[7 empty] | 2019-10-16 | 7 | 35
[7 empty] | 2019-10-17 | 8 | 40
[7 empty] | 2019-10-18 | 9 | 45
[7 empty] | 2019-10-19 | 10 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow |  | 2019-10-20 | 11 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful |  | 2019-10-21 | 12
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful |  | 2019-10-22 | 13
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral |  | 2019-10-23 | 14
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful |  | 2019-10-24 | 15
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful |  | 2019-10-25 | 16
| Test syntax | Syntax flaws in the test code |  | 6 |  |  | 2019-10-26 | 17
| Test logic | Logic flaws in the test code |  | 7 |  |  | 2019-10-27 | 18
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  |  | 2019-10-28 | 19
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  |  | 2019-10-29 | 20
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  |  | 2019-10-30 | 21
Y/N: | Yes |  |  | Passed |  |  | 2019-10-31 | 22
| No |  |  | Passed with issues |  |  | 2019-11-01 | 23
Proxy Types: | - |  |  | Failed | Base |  | 2019-11-02
| Calculation |  |  | Not tested | New |  | 2019-11-03
| Data |  |  | Not applicable | Reusable |  | 2019-11-04
| I/O | [5 empty] | 2019-11-05
| Logic | [5 empty] | 2019-11-06
2019-11-07
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
VL
<-- Mandatory |  | ✔